## Cutover Plan
ESB/POS Stage_ Network Cutover Breakdown List
Cutover Prerequisites
# | Operate Item | Owner | Thur 6/10/21 | Complete status
1 | Check Network connection from IDC to alicloud | Yu DongDong | 12:00-18:00
2 | Check SMC sync status | Yu DongDong | 12:00-18:00
Cutover Breakdown List
1 | Stage ESB/POS cutover | Owner | Thur 6/10/21 | Thur 6/10/21
1.1 | Shutdown of ESB application at IDC | TangMin | 18:00 | 18:20
1.2 | Sync data，Create the ESB VM in AliCloud | DongDong | 18:20 | 22:30
1.3 | Shutdown of POS application at IDC | Wee Sern | 20:00 | 20:20
1.4 | Sync data，Create POS VM in AliCloud | Yu DongDong | 20:20 | 22:30
1.5 | Check if Sync data is completed | Yu DongDong | 22:30 | 10:40
1.6 | Inform LVMH network team that network changes can start at 23:00 | Alan/Xia XiaoGuo | 22:40 | 22:50
1.7 | LVMH network team add route | LVMH network team | 23:00 | 23:30
1.8 | Release network route (10.157.48.0/24,10.157.49.0/24) in IDC | Network Team/Lemon | 23:00 | 23:30
1.9 | verfiy Network connetction (Make sure we cann't ping IDC POS/ESB IP) | Network Team/Lemon | 23:25 | 23:30
1.1 | Add route in POS/ESB of VPC in AliCloud | Xu HongMing | 23:30 | 23:40
1.11 | Modify AWS Tunnel IP For site to site VPN(Alicloud->AWS) | LiYang | 23:00 | 23:15
1.12 | Verify network connectivity in Alicloud | TangMin/Wee Sern/Dongdong | 23:30 | 23:59
| Login a server in alicloud | Yu DongDong | 23:30 | 23:59
| Test S2S VPN Connection curl http://sephora-esb-asia-sap-internal.k8s-staging.luxola.com/ | Yu DongDong | 23:30 | 23:59
2 | RollBack （If Network have issue canot be resloved,rollback this change) |  | Fir 6/11/21 | Fir 6/11/21
2.1 | Rollback network route (add route 10.157.48.0/24,10.157.49.0/24 in IDC | Network Team/Lemon | 1:00 | 1:30
2.2 | Rollback network route | LVMH network team | 1:00 | 1:30
2.3 | Remove route in POS/ESB of VPC in AliCloud | Xu HongMing | 1:00 | 1:30
2.4 | Delete S2S VPN in AliCloud | Liyang | 1:00 | 1:30
2.5 | Start ESB/POS application/Verify network connectivity in IDC/check ESB application status | TangMin /Wee Sern | 1:30 | 2:00

## Server List
P/V | Environment | Source-Host Name | Application | Component | Source-OS | Source-IP Address | Source-CPU | Source-Memory | Target-Host Name | Target-IP | Target-OS
V | GK-stage | SAS-SZ1WTNPS1 | NewPOS | TxCollector | Windows 2016 server | 10.157.48.60 | 16 | 64 | SAS-SZ1WTNPS1 | 10.157.48.59 | Windows 2016 server
V | GK-stage | SAS-SZ1WTNPS2 | NewPOS | TPAdmin | Windows 2016 server | 10.157.48.61 | 16 | 64 | SAS-SZ1WTNPS2 | 10.157.48.60 | Windows 2016 server
V | GK-stage | SAS-SZ1WTNPS3 | NewPOS | MSSQL 2016 | Windows 2016 server | 10.157.49.60 | 16 | 64 | SAS-SZ1WTNPS3 | 10.157.49.60 | Windows 2016 server
P/V | Environment | Source-Host Name | Application | Component | Source-OS | Source-IP Address | Source-CPU | Source-Memory | Target-Host Name | Target-IP | Target-OS
V | GK-stage | SAS-SZ1LDESB1 | ESB | IS + MWS | RHEL 7.4 | 10.157.48.129 | 4 | 16 | SAS-SZ1LDESB1 | 10.157.48.129 | RHEL 7.4
V | GK-stage | SAS-SZ1WDESB3 | ESB | MSSQL 2016 | Windows Server 2012 R2 | 10.157.49.129 | 4 | 8 | SAS-SZ1WDESB3 | 10.157.49.129 | Windows Server 2012 R2
V | GK-stage | SAS-SZ1LDESB4 | ESB | MongDB | RHEL 7.4 | 10.157.49.130 | 4 | 8 | SAS-SZ1LDESB4 | 10.157.49.130 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB13 | ESB | SFTP/VSFTP | RHEL 7.4 | 10.157.48.6 | 2 | 2 | SAS-SZ1LTESB13 | 10.157.48.6 | RHEL 7.4
V | GK-stage | SAS-SZ1LDESB2 | ESB | UM | RHEL 7.4 | 10.157.48.130 | 2 | 16 | SAS-SZ1LDESB2 | 10.157.48.130 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB7 | ESB | UM(主) | RHEL 7.4 | 10.157.48.4 vip 10.157.48.7 | 2 | 16 | SAS-SZ1LTESB7 | 10.157.48.4 vip 10.157.48.7 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB8 | ESB | UM(备) | RHEL 7.4 | 10.157.48.5 vip 10.157.48.7 | 2 | 16 | SAS-SZ1LTESB8 | 10.157.48.5 vip 10.157.48.7 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB10 | ESB | MongoDB | RHEL 7.4 | 10.157.49.3 | 4 | 8 | SAS-SZ1LTESB10 | 10.157.49.3 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB11 | ESB | MongoDB | RHEL 7.4 | 10.157.49.4 | 4 | 8 | SAS-SZ1LTESB11 | 10.157.49.4 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB12 | ESB | MongoDB | RHEL 7.4 | 10.157.49.5 | 4 | 8 | SAS-SZ1LTESB12 | 10.157.49.5 | RHEL 7.4
| GK-stage | SAS-SZ1LTESB5 | ESB | IS+TC+MWS | RHEL 7.4 | 10.157.48.2 | 4 | 32 | Replace with SLB
V | GK-stage | SAS-SZ1LTESB6 | ESB | IS+TC+MWS | RHEL 7.4 | 10.157.48.3 | 4 | 32 | SAS-SZ1LTESB6 | 10.157.48.3 | RHEL 7.4
V | GK-stage | SAS-SZ1LTESB20 | ESB | HA SQL SERVER | Windows Server 2016 | 10.157.49.6 | 8 | 16 | Replace with RDS
V | GK-stage | SAS-SZ1LTESB21 | ESB | HA SQL SERVER | Windows Server 2016 | 10.157.49.7 | 8 | 16 | Replace with RDS